## DVP
Efficycle Design Validation Plan
Team Name | [7 empty] | Target Vehicle Completion Date
INVINCIBLES3.0 | [7 empty] | 2019-08-28
Sr. No. | Subsystem | Part/Parameter Under Validation | Responsible | Design/Performance Requirement | Validation Method | Equipment/ Instrument used | No. of Trials/ Fequency | Validation Test Observations | Result | Remarks
1 | Frame | Weld Quality | Aarif | No Cracks should be present at the frame members & weld joints | Visual check of all frame members and joints | NA | one time |  | Pass/Fail
2 | Weight | Weight of the Vehicle | Nandini | Weight<150 kgs | Vehicle is weighed on three weighing machines on three wheels | 3 weighing machines | one time | W=
3 | Dimension | Length | Spurthi and Amitesh | Length<100" | Check the length between front and rear projected parts | Measuring tape | one time |  | 55"
4 |  | Width |  | Width<60" | Check the length between extreme right and left projected parts |  |  |  | 53"
5 |  | Seat height |  | Seat height<24" | Check the distance from point A to ground |  |  |  | 23"
6 |  | Sitting space height |  | Sitting space height=40" | Check the distance between point A and point B |  |  |  | 40"
7 |  | Seat Inclination |  | Angle=15 degrees with vertical | Check the angle between vetical and leaning member | Inclinometer |  |  | 15"
8 | Fork fittings | Bearings | Ramsai | Enable rotational movement while reducing friction | Checked after some run | Thermometer(comparing temperature to that of normal) | Three times |  | Pass/Fail
9 | Fasteners | Grip | Tejaswi | Should hold two different materials | Check after some run | Torque wrench | Three times |  | Pass/Fail
10 | Wheels | Load bearing capacity | Uday | Should withstand weight of vehicle in static and dynamic conditions | Check after some run | NA | Three times |  | Pass/Fail
11 | Steering | Turning radius | Sohan and Tejaswi | Turning Radius < 4m | Figure of 8 with turning radius | Measuring Tape , Stop Watch , Figure of 8 Test Track to be made as per rulebook | Minimum 3 trials |  | Radius=
12 | Suspension | Spring | Surabhi and Krishna | Absorb and reduce the excess energy from road to vehicle | Check the compression length when the load is applied | Scale , Spring balance | Three times |  | x average=
13 | Battery | Charging time | keerthana | Charging time should be < 11hrs | Check terminal voltage before and after 11 hrs. | Multimetre , stopwatch | One time |  | T charging=
15 |  | Leakage check | keerthana | No leakage from battery in static and dynamic conditions | Tilt battery on all 6 sides by not more than 45 deg,hold for 10sec | Stopwatch | Ten times |  | Pass/Fail
16 |  |  |  |  | Check battery each time when vehicle runs >1km | NA |  |  | Pass/Fail
17 | Braking system | Stopping distance | Ramsai and Aarif | Human drive <5m @ Maximum Velocity | Vehicle is made to run 50m in 10s | Measuring tape,stopwatch | Five times | D(stopping)= | Pass/Fail | Maximum Velocity = …m/s
18 |  |  |  | Electric drive<5m
19 |  | Brake force distribution |  | All brakes should work at same time and vehicle should go straight | Perpendicular lines marked on track,deviation on LH/RH<300mm | Try square,scale | Five times |  | Pass/Fail
20 | Transmission | Gradeability | Vaishnavi | Must be greater than 5 degrees | Load is kept on vehicle to have the same affect as grade and vehicle is made to run and time is calculated | Stopwatch | Eight times | t1=……….. | 15 sec | Max acc=……m/s2
21 |  | Maximum acceleration | Sohan | Should travel maximum laps in 2 hours in endurance run , acceleration test | Vehicle is made to run for 2hours | Measuring tape,stopwatch | Ten times | a1=….,a2=,…. | a avg=