## 1. Design Targets
Peformance Targets for Efficycle
Sr. No. | Items | Details
2 | Team Name | Invincibles 3.0
3 | Kerb Weight (kg | 150
4 | Length (mm): | 2540
5 | Length (inch): | 100
6 | Width (mm | 1524
7 | Width (Inch): | 60
8 | Height (mm): | 1651
9 | Height (inch): | 65
10 | Max speed (km/h | 40
11 | Maximum acceleration (m/s2): | 1.5
12 | Grade-abilit (degree): | 6.084
13 | Turning radius (m): | 4
14 | Turning radius (inch): | 157.48
15 | Battery Runime (Minutes): | 2hr30min

## 2. Project Plan
Efficycle Project Plan | [10 empty] | Legends |  |  | Main Task/ Activity
Sub Task/ Activity
|  |  |  | Team Name |  | Invincibles 3.0 | [7 empty] | Milestone
Milestone Details
Task ID | Task/Activity Description | Duration (Days) | Start Date | End Date | Responsible | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October
[6 empty] | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W44
[6 empty] | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 28
A | Design and Research | 39 | 2019-05-23 | 2019-06-30 | Spurthi
A.1 | Sub system Investigation | 11 | 2019-05-23 | 2019-06-02 | Nandini
A.2 | CAD Modelling | 7 | 2019-06-03 | 2019-06-09 | Spurthi
A.3 | Chasis Rollcage and Frame Desigining | 8 | 2019-10-03 | 2019-06-17 | Amitesh Jain
A.4 | Electrical Circuit Design | 10 | 2019-10-03 | 2019-06-19 | Sohanlal choudhary
A.5 | Analysis and Optimisation | 12 | 2019-06-19 | 2019-06-30 | Vaishnavi
B | Procurement | 40 | 2019-06-04 | 2019-07-16 | Krishna deshmukh
B.1 | Frame Material | 13 | 2019-06-04 | 2019-06-16 | Surabhi
B.2 | Electrical Circuit System | 12 | 2019-06-11 | 2019-06-22 | Keerthana
B.3 | Braking System | 10 | 2019-06-19 | 2019-06-28 | Ariff
B.4 | Steering System | 10 | 2019-06-26 | 2019-07-06 | Uday Aravind
B.5 | Gearing and Drive Train | 10 | 2019-07-06 | 2019-07-16 | Tejaswi
C | Fabrication | 60 | 2019-07-01 | 2019-07-29 | Ariff
C.1 | PVC Prototype | 8 | 2019-07-01 | 2019-07-08 | Ramsai
C.2 | Material Testing & Analysis | 8 | 2019-07-06 | 2019-07-13 | Krishna Deshmukh
C.3 | Assembly of drive components | 16 | 2019-07-14 | 2019-07-29 | Sohanlal choudhary
C.4 | Chasis Welding | 22 | 2019-07-26 | 2019-08-16 | Ariff
C.5 | Ergonomics | 8 | 2019-08-14 | 2019-08-21 | Spurthi
C.6 | Assembly of all components | 10 | 2019-08-20 | 2019-08-29 | Nandini
D | Testing and Completion | 30 | 2019-08-30 | 2019-08-28 | Keerthana
D.1 | Vehicle completion | 6 | 2019-08-30 | 2019-09-04 | Amitesh Jain
D.2 | Mock Dynamic Tests | 9 | 2019-09-05 | 2019-09-13 | Surabhi
D.3 | Working Inspection | 6 | 2019-09-14 | 2019-09-19 | Ramsai
D.4 | Static Evaluation | 9 | 2019-09-20 | 2019-09-28 | Nandini
Text
Efficycle Complete
Design Complete